## F04 - Voting & Comments
Filter by Pass / Fail
Risk ID | Scenario ID | Test Scenario | Test Case ID | Test Case Title | Priority | Test Design Technique | Preconditions | Test Data | Test Steps | Expected Result | Execution Status | Actual Result | Defect ID | Assumptions / Notes
VOTE-R01 | VOTE-TS01 | Prevent guest voting | VOTE-TC01 | Guest attempts vote | High | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Account: logged out | 1. Open car voting page. 2. attempt Vote. 3. inspect outcome. | No guest vote is recorded; login restriction is observable | Pass | No guest vote is recorded; login restriction is observable
VOTE-R02 | VOTE-TS02 | Prevent guest comments | VOTE-TC02 | Guest attempts comment | High | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Account: logged out; Comment: guest test | 1. Open car page. 2. attempt comment submission. | Guest comment is not published | Pass | Guest comment is not published
VOTE-R03 | VOTE-TS03 | Prevent repeated voting on same car | VOTE-TC03 | First eligible vote | High | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Fresh account with no vote on target car | 1. Log in. 2. open target car. 3. submit one vote. | Eligible vote is handled once with appropriate feedback | Pass | Eligible vote is handled once with appropriate feedback |  | Account used : HugoTan631@gmail.com Password : HugoTan631@gmail.com123 Target Car : Lamborghini Diablo
VOTE-R03 | VOTE-TS03 | Prevent repeated voting on same car | VOTE-TC04 | Immediate post-login voting state | High | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Fresh account with no vote on target car | 1. Open car page while logged out. 2. log in on same page. 3. inspect voting state before refreshing. | Voting eligibility reflects actual account vote history | Pass | Voting eligibility reflects actual account vote history
VOTE-R03 | VOTE-TS03 | Prevent repeated voting on same car | VOTE-TC05 | Second vote without refresh | High | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Account has just voted for target car | 1. Attempt another vote on same page. | Second vote is prevented | Pass | Second vote is prevented
VOTE-R04 | VOTE-TS04 | Persist vote restriction after refresh/navigation | VOTE-TC06 | Vote restriction after refresh | High | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Account already voted for target car | 1. Refresh target car page. 2. inspect controls. 3. attempt vote again. | Previous vote remains enforced | Pass | Previous vote remains enforced |  | Account used : HugoTan631@gmail.com Password : HugoTan631@gmail.com123 Target Car : Lamborghini Diablo
VOTE-R04 | VOTE-TS04 | Persist vote restriction after refresh/navigation | VOTE-TC07 | Vote restriction after revisit | High | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Account already voted for target car | 1. Navigate away. 2. return to same car. 3. attempt vote again. | Previous vote remains enforced | Pass | Previous vote remains enforced |  | Account used : HugoTan631@gmail.com Password : HugoTan631@gmail.com123 Target Car : Lamborghini Diablo
VOTE-R05 | VOTE-TS05 | Prevent actions after logout | VOTE-TC08 | Vote after logout | High | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Account logged in on car page | 1. Log out. 2. without refreshing 3. attempt vote. | Unauthenticated vote is rejected | Pass | Unauthenticated vote is rejected |  | Account used : HugoTan631@gmail.com Password : HugoTan631@gmail.com123 Target Car : Lamborghini Diablo
VOTE-R05 | VOTE-TS05 | Prevent actions after logout | VOTE-TC09 | Vote after logout and refresh | High | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Account logged out after authenticated visit | 1. Refresh car page. 2. attempt vote. | Unauthenticated vote is rejected | Pass | Unauthenticated vote is rejected
VOTE-R06 | VOTE-TS06 | Handle long comments without broken layout | VOTE-TC10 | Long comment layout | Medium | Exploratory | Car Voting page [P-03] available; controlled test account and target car prepared. | Long synthetic comment (e.g. 500 characters) | 1. Log in. 2. enter long comment. 3. submit if allowed. 4. inspect display. | Validation or rendering does not overflow or break page | Fail | Page width stretches as long as entered sentences Special symbols can overflow the row height | VOTE-DF01 | Length is a probe, not assumed limit
VOTE-R07 | VOTE-TS07 | Safely render unusual comment characters | VOTE-TC11 | Special symbols in comments | Medium | Exploratory | Car Voting page [P-03] available; controlled test account and target car prepared. | Comment: !@#$%^&*()<>? | 1. Log in. 2. enter symbols. 3. submit. 4. inspect rendered content. | Content is handled as text; no markup execution | Pass | Content is handled as text; no markup execution
VOTE-R08 | VOTE-TS08 | Update displayed vote count | VOTE-TC12 | Vote count change | High | Functional | Car Voting page [P-03] available; controlled test account and target car prepared. | Known pre-vote count; eligible account | 1. Record count. 2. vote once. 3. check count after UI settles. | Count reflects one successful vote, not more | Pass | Count reflects one successful vote, not more
VOTE-R09 | VOTE-TS09 | Persist comments and attribution | VOTE-TC13 | Comment persists after refresh | Medium | State Transition | Car Voting page [P-03] available; controlled test account and target car prepared. | Comment: QA unique timestamp-free marker; test account | 1. Post unique comment. 2. refresh. 3. locate comment. | Successfully submitted comment persists with correct author | Pass | Successfully submitted comment persists with correct author
VOTE-R09 | VOTE-TS09 | Persist comments and attribution | VOTE-TC14 | Comment metadata displayed | Medium | Functional | Car Voting page [P-03] available; controlled test account and target car prepared. | Test account; posted comment | 1. Submit unique comment. 2. inspect displayed author and any date/time. | Attribution matches account; displayed metadata is internally consistent | Fail | Metadata displayed. Author not displayed | VOTE-DF02 | Only assert timestamp if interface supplies one
VOTE-R10 | VOTE-TS10 | Show submission confirmation | VOTE-TC15 | Vote success feedback | Medium | Functional | Car Voting page [P-03] available; controlled test account and target car prepared. | Eligible account | 1. Submit one vote. 2. inspect notification. | Clear success or failure outcome is displayed | Pass | Clear success or failure outcome is displayed
VOTE-R10 | VOTE-TS10 | Show submission confirmation | VOTE-TC16 | Comment submission feedback | Medium | Functional | Car Voting page [P-03] available; controlled test account and target car prepared. | Valid comment and logged-in account | 1. Submit comment. 2. inspect response. | Submission outcome is communicated clearly | Pass | Submission outcome is communicated clearly

## F01 - Authentication
Risk ID | Scenario ID | Test Scenario | Test Case ID | Test Case Title | Priority | Test Design Technique | Preconditions | Test Data | Test Steps | Expected Result | Execution Status | Actual Result | Defect ID | Assumptions / Notes
AUTH-R01 | AUTH-TS01 | Verify credential fields accept user entry | AUTH-TC01 | Login field accepts input | High | Functional | Application reachable; user logged out; login form visible. | Username: qa_valid_user | 1. Focus Login field. 2. Type test username. 3. Observe displayed text. | Login field accepts the typed value and remains editable. | Not Run |  |  | Replace placeholder with a dedicated registered test account.
AUTH-R01 | AUTH-TS01 | Verify credential fields accept user entry | AUTH-TC02 | Password field accepts and masks input | High | Functional | Application reachable; user logged out; login form visible. | Password: valid account password | 1. Focus Password field. 2. Type test password. 3. Observe field presentation. | Password input accepts characters without exposing them as ordinary visible text. | Not Run
AUTH-R02 | AUTH-TS02 | Verify login submission control functions | AUTH-TC03 | Submit with Login button | High | Functional | Application reachable; user logged out; login form visible. Valid credentials entered. | Registered username and matching password | 1. Enter valid credentials. 2. Click Login once. 3. Observe response. | Login action is processed and authentication outcome is shown; no unresponsive button. | Not Run |  |  | Use a fresh logged-out state.
AUTH-R03 | AUTH-TS03 | Verify invalid or missing credentials are rejected | AUTH-TC04 | Valid username, wrong password | Critical | Decision Table | Application reachable; user logged out; login form visible. Dedicated account exists. | Registered username; nonmatching password | 1. Enter registered username. 2. Enter incorrect password. 3. Click Login. | Authentication is rejected; authenticated-only controls are not granted. | Not Run
AUTH-R03 | AUTH-TS03 | Verify invalid or missing credentials are rejected | AUTH-TC05 | Unknown username, known password | Critical | Decision Table | Application reachable; user logged out; login form visible. Dedicated account exists. | Unregistered username; password from test account | 1. Enter unknown username. 2. Enter known test password. 3. Click Login. | Authentication is rejected; authenticated-only controls are not granted. | Not Run
AUTH-R03 | AUTH-TS03 | Verify invalid or missing credentials are rejected | AUTH-TC06 | Unknown username and wrong password | Critical | Decision Table | Application reachable; user logged out; login form visible. | Unregistered username; incorrect password | 1. Enter unknown username. 2. Enter incorrect password. 3. Click Login. | Authentication is rejected; authenticated-only controls are not granted. | Not Run
AUTH-R03 | AUTH-TS03 | Verify invalid or missing credentials are rejected | AUTH-TC07 | Blank username | Critical | Equivalence Partitioning | Application reachable; user logged out; login form visible. | Username: blank; Password: valid account password | 1. Leave Login blank. 2. Enter password. 3. Click Login. | No authenticated session is established; missing username is handled. | Not Run
AUTH-R03 | AUTH-TS03 | Verify invalid or missing credentials are rejected | AUTH-TC08 | Blank password | Critical | Equivalence Partitioning | Application reachable; user logged out; login form visible. | Username: registered; Password: blank | 1. Enter registered username. 2. Leave Password blank. 3. Click Login. | No authenticated session is established; missing password is handled. | Not Run
AUTH-R03 | AUTH-TS03 | Verify invalid or missing credentials are rejected | AUTH-TC09 | Both credentials blank | Critical | Equivalence Partitioning | Application reachable; user logged out; login form visible. | Username: blank; Password: blank | 1. Leave both fields blank. 2. Click Login. | No authenticated session is established; empty submission is handled. | Not Run
AUTH-R04 | AUTH-TS04 | Verify valid credentials authenticate | AUTH-TC10 | Valid username and matching password | High | Decision Table | Application reachable; user logged out; login form visible. Dedicated active account exists. | Registered username; matching password | 1. Enter matching credentials. 2. Click Login. 3. Observe UI. | User is authenticated; logged-in identity or controls become available. | Not Run
AUTH-R05 | AUTH-TS05 | Verify failed login feedback is clear | AUTH-TC11 | Feedback for incorrect password | Medium | Functional | Application reachable; user logged out; login form visible. Dedicated account exists. | Registered username; wrong password | 1. Enter registered username. 2. Enter wrong password. 3. Click Login. 4. Read feedback. | A clear failure indication is displayed without claiming login succeeded. | Not Run |  |  | Exact message wording is not specified.
AUTH-R05 | AUTH-TS05 | Verify failed login feedback is clear | AUTH-TC12 | Feedback for missing credentials | Medium | Equivalence Partitioning | Application reachable; user logged out; login form visible. | Both fields blank | 1. Leave fields blank. 2. Click Login. 3. Inspect feedback. | Submission is rejected or prevented with understandable feedback. | Not Run |  |  | UI may use browser-native or application validation.
AUTH-R06 | AUTH-TS06 | Verify successful login updates authenticated UI state | AUTH-TC13 | Authenticated controls update after login | Medium | State Transition | Application reachable; user logged out; login form visible. Dedicated account exists. | Registered username; matching password | 1. Note logged-out navigation controls. 2. Log in. 3. Compare visible navigation and account controls. | UI reflects logged-in state, such as account identity and Logout access. | Not Run |  |  | Do not assume a specific redirect unless documented.
AUTH-R06 | AUTH-TS06 | Verify successful login updates authenticated UI state | AUTH-TC14 | Login state from multiple supported pages | Medium | State Transition / Data-Driven | Application reachable; user logged out; login form visible. Identify pages with login form. | P-01, P-02, P-03, P-05, P-06 (where login available) | 1. On each applicable page, begin logged out. 2. Log in using valid credentials. 3. Record resulting page, controls and session state. 4. Log out before next iteration. | Login succeeds and authenticated state is consistent on each applicable page. | Not Run |  |  | Record each page iteration separately; redirect destination requires confirmation.

## F02 - Registration
Risk ID | Scenario ID | Test Scenario | Test Case ID | Test Case Title | Priority | Test Design Technique | Preconditions | Test Data | Test Steps | Expected Result | Execution Status | Actual Result | Defect ID | Assumptions / Notes
REG-R01 | REG-TS01 | Check required first and last name validation | REG-TC01 | Blank first name | Medium | EP | Registration page [P-05] open; unique synthetic account details available. | First Name: blank; other required fields: valid | 1. Leave First Name empty. 2. fill remaining fields. 3. click Register. | Missing required name is identified; no account is created | Not Run
REG-R01 | REG-TS01 | Check required first and last name validation | REG-TC02 | Blank last name | Medium | EP | Registration page [P-05] open; unique synthetic account details available. | Last Name: blank; other required fields: valid | 1. Leave Last Name empty. 2. fill remaining fields. 3. click Register. | Missing required name is identified; no account is created | Not Run
REG-R02 | REG-TS02 | Check valid names are accepted | REG-TC03 | Ordinary alphabetic names | Medium | EP | Registration page [P-05] open; unique synthetic account details available. | First: Jamie; Last: Tan | 1. Enter names. 2. complete remaining fields. 3. submit. | Valid names are accepted without unrelated name errors | Not Run
REG-R02 | REG-TS02 | Check valid names are accepted | REG-TC04 | Names with spaces or hyphens | Medium | Exploratory | Registration page [P-05] open; unique synthetic account details available. | First: Anne-Marie; Last: Van Dyke | 1. Enter names. 2. complete form. 3. submit. | Observe whether names are accepted and record any stated rule | Not Run
REG-R03 | REG-TS03 | Check duplicate identifiers are rejected | REG-TC05 | Duplicate login identifier | High | EP | Registration page [P-05] open; unique synthetic account details available. | Login: existing registered username | 1. Enter already-registered login. 2. complete other fields with valid unique data. 3. submit. | Duplicate account is not silently created; clear response is displayed | Not Run
REG-R03 | REG-TS03 | Check duplicate identifiers are rejected | REG-TC06 | Duplicate email identifier, if distinct | High | EP | Registration page [P-05] open; unique synthetic account details available. | Email: existing registered email | 1. If a separate email field exists, enter existing email. 2. complete form. 3. submit. | Existing unique identifier cannot create conflicting duplicate account | Not Run |  |  | Only execute if distinct email field exists
REG-R04 | REG-TS04 | Check invalid login/email formats | REG-TC07 | Malformed identifier | High | EP | Registration page [P-05] open; unique synthetic account details available. | Login/email: invalid-email-format | 1. Enter malformed value. 2. complete remaining fields. 3. submit. | Validation behaviour is recorded against documented format requirements | Not Run |  |  | Confirm whether Login is a username or email before treating format as mandatory
REG-R05 | REG-TS05 | Check valid login/email formats | REG-TC08 | Supported valid identifier | High | EP | Registration page [P-05] open; unique synthetic account details available. | Login: unique valid identifier | 1. Enter a supported identifier. 2. complete form. 3. submit. | Valid identifier does not cause a format-related rejection | Not Run
REG-R06 | REG-TS06 | Check password rule validation | REG-TC09 | Empty password | High | EP | Registration page [P-05] open; unique synthetic account details available. | Password: blank; Confirm: blank | 1. Complete all other required fields. 2. leave password blank. 3. submit. | Required password validation prevents unintended account creation | Not Run
REG-R06 | REG-TS06 | Check password rule validation | REG-TC10 | Candidate weak password | High | EP | Registration page [P-05] open; unique synthetic account details available. | Password: 123; Confirm: 123 | 1. Complete form with candidate weak password. 2. submit. | Compare acceptance with observed or documented password policy | Not Run |  |  | Do not assume minimum length/complexity without evidence
REG-R07 | REG-TS07 | Check compliant passwords are accepted | REG-TC11 | Valid password | Medium | EP | Registration page [P-05] open; unique synthetic account details available. | Password: known accepted password; Confirm: same | 1. Enter accepted password in both fields. 2. complete form. 3. submit. | Password passes validation | Not Run |  |  | Confirm accepted password policy from observed behaviour
REG-R08 | REG-TS08 | Check password confirmation matching | REG-TC12 | Mismatched confirmation | High | Decision Table | Registration page [P-05] open; unique synthetic account details available. | Password: ValidPassA!; Confirm: ValidPassB! | 1. Enter differing password values. 2. complete form. 3. submit. | Mismatched confirmation is rejected | Not Run
REG-R08 | REG-TS08 | Check password confirmation matching | REG-TC13 | Matching confirmation | High | Decision Table | Registration page [P-05] open; unique synthetic account details available. | Password: accepted value; Confirm: identical value | 1. Enter identical accepted values. 2. complete form. 3. submit. | Confirmation match does not block valid registration | Not Run
REG-R09 | REG-TS09 | Check unusual characters are handled safely | REG-TC14 | Special characters in name | High | Exploratory | Registration page [P-05] open; unique synthetic account details available. | First: O'Neil; Last: Test | 1. Enter name containing apostrophe. 2. submit completed form. | Input is safely handled; no script execution or page failure | Not Run
REG-R09 | REG-TS09 | Check unusual characters are handled safely | REG-TC15 | HTML-like text in input | High | Exploratory | Registration page [P-05] open; unique synthetic account details available. | First: <b>Test</b> | 1. Enter literal HTML-like text in field. 2. submit. | Input is treated as data; no markup execution or UI crash | Not Run
REG-R10 | REG-TS10 | Check registration validation feedback | REG-TC16 | Multiple invalid fields | Medium | Functional | Registration page [P-05] open; unique synthetic account details available. | First: blank; Password: blank | 1. Leave two required fields empty. 2. submit. | Actionable validation feedback is visible | Not Run
REG-R11 | REG-TS11 | Check valid account registration | REG-TC17 | Register unique account | High | Workflow | Registration page [P-05] open; unique synthetic account details available. | All fields: unique, valid synthetic values | 1. Enter unique test data. 2. click Register. 3. inspect confirmation. 4. attempt login with new account. | Registration outcome is observable and successful account can authenticate | Not Run
REG-R12 | REG-TS12 | Check Register submission control | REG-TC18 | Register button responds | High | Functional | Registration page [P-05] open; unique synthetic account details available. | All fields: valid synthetic values | 1. Complete form. 2. click Register once. 3. observe UI. | Click triggers visible processing or validation; not inert | Not Run

## F03 - Car Browsing
Risk ID | Scenario ID | Test Scenario | Test Case ID | Test Case Title | Priority | Test Design Technique | Preconditions | Test Data | Test Steps | Expected Result | Execution Status | Actual Result | Defect ID | Assumptions / Notes
BROWSE-R01 | BROWSE-TS01 | Check car image matches model name | BROWSE-TC01 | Image and model association | Medium | Functional | Application available; required listing/detail page loaded. | Known car listing: Lamborghini Diablo | 1. Open listing. 2. read model name. 3. compare visible image with identified model. | Displayed model and picture are consistent with verified reference | Not Run |  |  | Use reliable model reference, not appearance guess alone
BROWSE-R02 | BROWSE-TS02 | Check car selection opens corresponding detail | BROWSE-TC02 | Select model from Home | High | Workflow | Application available; required listing/detail page loaded. | Model: Diablo | 1. Open Home. 2. click selected model. 3. check destination heading/details. | Correct model detail page is shown | Not Run
BROWSE-R02 | BROWSE-TS02 | Check car selection opens corresponding detail | BROWSE-TC03 | Select model from Popular Make | High | Workflow | Application available; required listing/detail page loaded. | Model: visible model entry | 1. Open Popular Make. 2. select a model. 3. compare destination. | Selected model and destination match | Not Run
BROWSE-R03 | BROWSE-TS03 | Check View More opens intended model | BROWSE-TC04 | View More link target | High | Functional | Application available; required listing/detail page loaded. | Card: identified car model | 1. Locate View More for specific card. 2. click. 3. compare destination model. | Detail matches selected card | Not Run
BROWSE-R04 | BROWSE-TS04 | Check Next/Previous changes listings | BROWSE-TC05 | Next pagination changes records | Medium | State Transition | Application available; required listing/detail page loaded. | Listing with multiple pages | 1. Record visible items. 2. click Next. 3. compare item set and page indicator. | Next page shows intended subsequent records | Not Run
BROWSE-R04 | BROWSE-TS04 | Check Next/Previous changes listings | BROWSE-TC06 | Previous returns records | Medium | State Transition | Application available; required listing/detail page loaded. | Listing after Next | 1. Record current page. 2. click Previous. 3. compare with original. | Previous returns expected earlier records | Not Run
BROWSE-R05 | BROWSE-TS05 | Check pagination continuity | BROWSE-TC07 | No duplicates across adjacent pages | Medium | Functional | Application available; required listing/detail page loaded. | Pages 1 and 2; stable dataset | 1. Record identifiers on page 1. 2. click Next. 3. record page 2. 4. compare. | No unexpected duplicated or omitted entries within stable ordered listing | Not Run |  |  | Check whether repeated items are intentionally pinned
BROWSE-R06 | BROWSE-TS06 | Check global navigation destinations | BROWSE-TC08 | Home navigation | High | Functional | Application available; required listing/detail page loaded. | Home link | 1. From detail page, click Home. 2. inspect page. | Navigates to Home | Not Run
BROWSE-R06 | BROWSE-TS06 | Check global navigation destinations | BROWSE-TC09 | Ranking navigation | High | Functional | Application available; required listing/detail page loaded. | Overall Rating link | 1. Click Overall Rating from supported page. | Navigates to ranking page | Not Run
BROWSE-R06 | BROWSE-TS06 | Check global navigation destinations | BROWSE-TC10 | Popular Make navigation | High | Functional | Application available; required listing/detail page loaded. | Popular Make link | 1. Click Popular Make from supported page. | Navigates to intended page | Not Run

## F05 - Profile
Risk ID | Scenario ID | Test Scenario | Test Case ID | Test Case Title | Priority | Test Design Technique | Preconditions | Test Data | Test Steps | Expected Result | Execution Status | Actual Result | Defect ID | Assumptions / Notes
PROF-R01 | PROF-TS01 | Check profile Save action | PROF-TC01 | Save valid profile edit | High | Functional | Logged in as controlled test account; Profile page [P-04] open. | Logged-in account; First Name: UpdatedName | 1. Open Profile. 2. change name. 3. click Save. 4. inspect feedback. | Valid edit is saved and shown | Not Run
PROF-R02 | PROF-TS02 | Check field input validation | PROF-TC02 | Reject invalid profile input | Medium | EP | Logged in as controlled test account; Profile page [P-04] open. | First Name: blank | 1. Open Profile. 2. clear name. 3. Save. | Validation behaviour matches required field rules | Not Run |  |  | Confirm field requiredness before recording failure
PROF-R03 | PROF-TS03 | Check age validation | PROF-TC03 | Negative age input | Medium | EP | Logged in as controlled test account; Profile page [P-04] open. | Age: -5 | 1. Open Profile. 2. set age to -5. 3. Save. | Invalid negative age is rejected or prevented | Not Run
PROF-R03 | PROF-TS03 | Check age validation | PROF-TC04 | Unusually high age input | Medium | Exploratory | Logged in as controlled test account; Profile page [P-04] open. | Age: 200 | 1. Open Profile. 2. set age to 200. 3. Save. | Check observed validation against documented range; do not presume maximum | Not Run |  |  | Upper limit unconfirmed
PROF-R04 | PROF-TS04 | Check gender field behaviour | PROF-TC05 | Gender selection persists | Medium | Functional | Logged in as controlled test account; Profile page [P-04] open. | Gender: selectable value | 1. Select available gender option. 2. Save. 3. reload. | Selected value is stored and displayed | Not Run
PROF-R05 | PROF-TS05 | Check dropdown input restrictions | PROF-TC06 | Dropdown disallows unsupported options | Medium | Functional | Logged in as controlled test account; Profile page [P-04] open. | Dropdown: unsupported free text | 1. Open Profile. 2. attempt to enter value not in dropdown. | Dropdown enforces its actual available choices | Not Run |  |  | Only if rendered as selection control
PROF-R06 | PROF-TS06 | Check Cancel action | PROF-TC07 | Cancel discards unsaved edits | Medium | State Transition | Logged in as controlled test account; Profile page [P-04] open. | Name: UnsavedEdit | 1. Record original. 2. edit. 3. click Cancel. 4. reopen/reload. | Unsaved change is not committed | Not Run
PROF-R07 | PROF-TS07 | Check saved profile persistence | PROF-TC08 | Saved data persists on revisit | High | State Transition | Logged in as controlled test account; Profile page [P-04] open. | Valid edited profile field | 1. Save edit. 2. navigate away. 3. return. | Saved value persists | Not Run
PROF-R08 | PROF-TS08 | Check profile data retrieval | PROF-TC09 | Existing profile loads | Medium | Functional | Logged in as controlled test account; Profile page [P-04] open. | Known registered account profile | 1. Log in. 2. open Profile. 3. inspect fields. | Fields display account-associated values | Not Run
PROF-R09 | PROF-TS09 | Check login identifier editability | PROF-TC10 | Login field editability | Medium | Functional | Logged in as controlled test account; Profile page [P-04] open. | Login identifier | 1. Open Profile. 2. attempt to edit Login field. | Behaviour matches identifier editability rule; unexpected mutation is prevented | Not Run |  |  | Confirm whether field is designed read-only

## F06 - Password Management
Risk ID | Scenario ID | Test Scenario | Test Case ID | Test Case Title | Priority | Test Design Technique | Preconditions | Test Data | Test Steps | Expected Result | Execution Status | Actual Result | Defect ID | Assumptions / Notes
PASS-R01 | PASS-TS01 | Check current password verification | PASS-TC01 | Wrong current password | High | Decision Table | Logged in with disposable test account; current password known; Profile page open. | Current: incorrect; New/Confirm: matching accepted value | 1. Open Profile. 2. fill password change fields. 3. Save. | Password change rejected | Not Run
PASS-R01 | PASS-TS01 | Check current password verification | PASS-TC02 | Missing current password | High | EP | Logged in with disposable test account; current password known; Profile page open. | Current: blank; New/Confirm: matching accepted value | 1. Enter new/confirm. 2. leave current empty. 3. Save. | Password is not changed without required verification | Not Run
PASS-R02 | PASS-TS02 | Check new and confirm password match | PASS-TC03 | Mismatched new confirmation | High | Decision Table | Logged in with disposable test account; current password known; Profile page open. | Current: correct; New: A; Confirm: B | 1. Enter different new/confirm values. 2. Save. | Mismatched values are rejected | Not Run
PASS-R03 | PASS-TS03 | Check unsupported/weak new passwords | PASS-TC04 | Candidate weak new password | High | EP | Logged in with disposable test account; current password known; Profile page open. | Current: correct; New/Confirm: 123 | 1. Fill fields. 2. Save. 3. compare result with known rules. | Password acceptance matches established policy | Not Run |  |  | Policy limits unconfirmed; no invented minimum
PASS-R04 | PASS-TS04 | Check compliant password accepted | PASS-TC05 | Accepted new password | Medium | Functional | Logged in with disposable test account; current password known; Profile page open. | Current: correct; New/Confirm: verified accepted value | 1. Fill matching accepted new password. 2. Save. | Change succeeds and gives visible outcome | Not Run
PASS-R05 | PASS-TS05 | Check blank password fields preserve password | PASS-TC06 | Leave all password fields empty | High | EP | Logged in with disposable test account; current password known; Profile page open. | Current/New/Confirm: blank | 1. Edit non-password profile field. 2. leave password fields empty. 3. Save. 4. later re-login. | Existing password remains valid | Not Run |  |  | Confirm application blank-fields behaviour
PASS-R06 | PASS-TS06 | Check failure messages | PASS-TC07 | Wrong-current error feedback | Medium | Functional | Logged in with disposable test account; current password known; Profile page open. | Current: wrong; New/Confirm: matching | 1. Attempt update with wrong current password. 2. inspect message. | Clear failure response without implying change succeeded | Not Run
PASS-R07 | PASS-TS07 | Check new password works on next login | PASS-TC08 | New password works after logout | High | Workflow | Logged in with disposable test account; current password known; Profile page open. | New password from successful update | 1. Log out. 2. enter account name and new password. 3. Login. | New password authenticates | Not Run
PASS-R08 | PASS-TS08 | Check old password becomes invalid | PASS-TC09 | Old password rejected after change | High | Workflow | Logged in with disposable test account; current password known; Profile page open. | Old password before successful update | 1. Log out. 2. try old password. 3. inspect outcome. | Old password no longer authenticates | Not Run

## F07 - Ranking Management
Risk ID | Scenario ID | Test Scenario | Test Case ID | Test Case Title | Priority | Test Design Technique | Preconditions | Test Data | Test Steps | Expected Result | Execution Status | Actual Result | Defect ID | Assumptions / Notes
RANK-R01 | RANK-TS01 | Check descending vote-count order | RANK-TC01 | Descending counts allow ties | High | Functional | Relevant ranking and car detail pages accessible; capture counts close together. | Ranking rows and vote totals | 1. Open Overall Rating. 2. record visible vote counts. 3. compare consecutive rows. | Counts are non-increasing; ties allowed | Not Run
RANK-R02 | RANK-TS02 | Check displayed rank numbering | RANK-TC02 | Displayed rank sequence | Medium | Functional | Relevant ranking and car detail pages accessible; capture counts close together. | Ranking rows 1 onward | 1. Record rank labels and row positions. 2. compare. | Labels follow intended numbering scheme | Not Run |  |  | Ties may use shared ranks; verify intended convention
RANK-R03 | RANK-TS03 | Check counts across detail/ranking | RANK-TC03 | Ranking/detail count match | High | Functional | Relevant ranking and car detail pages accessible; capture counts close together. | Identified car visible in both views | 1. Record count on ranking. 2. open same car detail. 3. compare. | Same model shows consistent count after data settles | Not Run
RANK-R04 | RANK-TS04 | Check ranking after new vote | RANK-TC04 | Ranking responds to vote | High | Workflow | Relevant ranking and car detail pages accessible; capture counts close together. | Eligible test account and identified car | 1. Record initial rank/count. 2. vote once. 3. return to ranking. 4. refresh if necessary. | Count updates; position respects sort order | Not Run |  |  | Do not require position change if counts remain below adjacent cars
RANK-R05 | RANK-TS05 | Check ranking consistency across views | RANK-TC05 | Same-car totals across views | Medium | Functional | Relevant ranking and car detail pages accessible; capture counts close together. | Identical model shown in Home, Popular Make, Overall Rating | 1. Compare counts for same model at comparable time. | Vote totals agree for identical model | Not Run |  |  | Do not assume rank number is identical across different subsets

## F08 - Session & Logout
Risk ID | Scenario ID | Test Scenario | Test Case ID | Test Case Title | Priority | Test Design Technique | Preconditions | Test Data | Test Steps | Expected Result | Execution Status | Actual Result | Defect ID | Assumptions / Notes
SES-R01 | SES-TS01 | Check logout invalidates authentication | SES-TC01 | Logout ends authenticated access | High | State Transition | Controlled account and authenticated/unauthenticated states prepared. | Logged-in test account | 1. Log in. 2. click Logout. 3. attempt an authenticated-only action. | User is no longer authorized | Not Run |  |  | Do not require a specific cookie implementation
SES-R02 | SES-TS02 | Check protected data after logout | SES-TC02 | Cached profile visible after logout | High | State Transition | Controlled account and authenticated/unauthenticated states prepared. | Logged in on Profile | 1. Record profile display. 2. click Logout without refresh. 3. inspect screen and access. | Sensitive information is not newly retrievable as authenticated data; record stale display separately | Not Run |  |  | Cached text alone does not prove valid session
SES-R02 | SES-TS02 | Check protected data after logout | SES-TC03 | Direct profile revisit after logout | High | State Transition | Controlled account and authenticated/unauthenticated states prepared. | Logged-out after viewing Profile | 1. Navigate away. 2. attempt Profile URL/navigation. | Protected profile information is not freshly accessible | Not Run
SES-R03 | SES-TS03 | Check protected actions after logout | SES-TC04 | Profile Save after logout | High | State Transition | Controlled account and authenticated/unauthenticated states prepared. | Logged in on Profile | 1. Edit field. 2. log out without refresh. 3. click Save. | Change is not authorized or persisted | Not Run
SES-R03 | SES-TS03 | Check protected actions after logout | SES-TC05 | Vote after logout | High | State Transition | Controlled account and authenticated/unauthenticated states prepared. | Logged in on car page | 1. Log out. 2. attempt Vote without refreshing. | Vote is not recorded | Not Run
SES-R04 | SES-TS04 | Check logout from current page | SES-TC06 | Logout while on Profile | Medium | State Transition | Controlled account and authenticated/unauthenticated states prepared. | Logged in on Profile | 1. Click Logout. 2. observe location and controls. | Authenticated actions become unavailable even if page remains visible | Not Run |  |  | Redirect is not assumed mandatory
SES-R05 | SES-TS05 | Check browser refresh/back after logout | SES-TC07 | Refresh after logout | High | State Transition | Controlled account and authenticated/unauthenticated states prepared. | Logged-out session on prior protected page | 1. Refresh page. 2. inspect authentication controls and protected data. | Logged-out state remains enforced | Not Run
SES-R05 | SES-TS05 | Check browser refresh/back after logout | SES-TC08 | Back navigation after logout | High | State Transition | Controlled account and authenticated/unauthenticated states prepared. | Logged-out after profile visit | 1. Use browser Back. 2. inspect page. 3. try protected action. | History cache does not restore authorization | Not Run
SES-R06 | SES-TS06 | Check auth state consistency across pages | SES-TC09 | Auth state across pages | High | Workflow | Controlled account and authenticated/unauthenticated states prepared. | Logged in, then logged out | 1. Visit Home, car page, Profile as allowed. 2. compare login/logout controls before and after logout. | State is consistent and protected actions respect auth status | Not Run