## Risk Dashboard
Risk Assessment Criteria |  |  | Level | Likelihood | Impact | Priority
Likelihood | All |  | Low | Unlikely based on available evidence | Minor inconvenience | Can be tested later
Impact | ALL |  | Medium | Plausible but not observed | Disrupts functionality | Test after critical workflows
Priority | High |  | High | Already observed or supported by strong evidence | Prevents core functionality | Test early
|  |  | Critical | - | Security breach or major data exposure | Test immediately
|  |  | Unknown | Insufficient evidence | - | -
Risk ID | Likelihood | Priority | Impact | Risk / What Could Go Wrong | Rationale
AUTH-R01 | Low | High | High | User may be unable to enter credentials into the Login or Password fields | Prevents the user from attempting authentication
AUTH-R02 | Low | High | High | Login button may not initiate authentication when clicked | Prevents the user from submitting credentials
AUTH-R03 | Unknown | Critical | High | Invalid credential combinations may successfully authenticate the user | Could allow unauthorized access
AUTH-R04 | Medium | High | High | Valid credentials may fail to authenticate the user | Prevents legitimate users from accessing authenticated functionality
REG-R03 | Unknown | High | High | Registration may incorrectly handle duplicate user-identifying values | Could create conflicting accounts or incorrectly prevent legitimate registration
REG-R04 | Medium | High | High | Login/email field may accept invalidly formatted values | Could create accounts with unusable or invalid identifiers
REG-R05 | Medium | High | High | Valid login/email values may be incorrectly rejected | Could prevent legitimate users from registering
REG-R06 | Unknown | High | High | Password may accept values that do not satisfy required password rules | Could create accounts with passwords that violate the application's intended validation rules
REG-R08 | Medium | High | High | Password and Confirm Password may not be validated against each other | Could create an account with an unintended password or produce inconsistent registration behaviour
REG-R09 | Unknown | High | High | Registration inputs may not safely handle unexpected or malicious input | Unexpected input could cause incorrect behaviour, errors, or unsafe processing
REG-R11 | Medium | High | High | Valid registration details may fail to create an account | Prevents legitimate users from registering
REG-R12 | Low | High | High | Registration submission may fail to initiate when the Register button is used | Prevents users from completing registration
BROWSE-R02 | Medium | High | High | Selecting a car model may navigate to the wrong Car Voting page | User may view or interact with a different model than the one selected
BROWSE-R03 | Medium | High | High | View More may navigate to the wrong car model | User may access comments/details belonging to another model
BROWSE-R06 | Medium | High | High | Navigation links may leave the user on the current page or navigate to an incorrect page | Core application navigation may become unreliable
VOTE-R01 | Unknown | High | High | Unauthenticated users may be able to submit votes | Could allow unauthorized voting and compromise vote integrity
VOTE-R02 | Unknown | High | High | Unauthenticated users may be able to submit comments | Could allow unauthorized content submission
VOTE-R03 | High | High | High | An authenticated user may be able to vote for the same car model more than once when repeat voting is not permitted | Could manipulate vote counts and model rankings
VOTE-R04 | High | High | High | Voting restrictions may be bypassed by refreshing or leaving and returning to the page | Client/page state may reset while the underlying voting restriction should remain enforced
VOTE-R05 | Medium | High | High | A user who logs out while remaining on the Car Voting Page [P-03] may still be able to vote or comment | Previously loaded authenticated controls may remain usable after the session ends
VOTE-R08 | Medium | High | High | A submitted vote may not correctly update the displayed vote count | Users may see inaccurate voting information
PROF-R09 | Low | Medium | High | Read-only account information such as Login may be modified when it should not be editable | Account identifiers could be unintentionally changed
PASS-R01 | Unknown | High | High | Password may be changed without providing the correct current password | An unauthorized person with access to an active session could change the account password
PASS-R02 | Medium | High | High | New Password and Confirm Password may not be required to match | User could unknowingly set a password different from what they intended
PASS-R03 | Medium | High | High | Invalid or unsupported passwords may be accepted | Could allow passwords that violate the application's intended password rules
PASS-R05 | Medium | High | High | Empty password fields may unintentionally modify the existing password | The UI states “leave empty to keep current,” so leaving them empty should preserve the password
PASS-R07 | Medium | High | High | Password change may appear successful but the new password may not actually be stored | User could later be unable to authenticate using the expected new password
PASS-R08 | Medium | High | High | Old password may remain usable after a successful password change | Password update may not be applied correctly
RANK-R01 | Medium | High | High | Car rankings may not be sorted correctly according to vote count | Displayed ranking may not accurately represent the cars' vote totals
RANK-R03 | Medium | High | High | Vote count displayed in ranking pages may differ from the vote count on the corresponding Car Voting page | The same car may show inconsistent rating data across the application
RANK-R04 | Medium | High | High | Ranking may not update correctly after a new vote is submitted | Recently submitted votes may not be reflected in the displayed ranking
RANK-R05 | Medium | High | High | The same car may show different rank/vote information across Home, Popular Make and Overall Rating | Users may receive contradictory rating information depending on the page viewed
SES-R01 | Unknown | High | High | Logout may not properly terminate the authenticated session | User may remain authenticated after requesting logout
SES-R02 | High | High | High | Protected user information may remain visible after logout | Sensitive account information may remain accessible after the session ends
SES-R03 | Medium | High | High | User may still be able to perform authenticated actions after logout | Protected operations such as profile updates or voting could remain accessible
SES-R05 | Medium | High | High | Refreshing or revisiting a protected page after logout may restore authenticated access | Session termination may not persist correctly

## Overview
Feature ID | Feature | Relevant Pages
F-01 | Authentication | Home Page [P-01], Popular Make Page [P-02], Car Voting Page [P-03], Registration Page [P-05], Overall Rating Page [P-06]
F-02 | Registration | Registration Page [P-05]
F-03 | Car Browsing & Navigation | Home Page [P-01], Popular Make Page [P-02], Car Voting Page [P-03], Overall Rating Page [P-06]
F-04 | Voting & Comments | Car Voting Page [P-03]
F-05 | Profile Management | Profile Page [P-04]
F-06 | Password Management | Profile Page [P-04]
F-07 | Ranking / Rating Display | Home Page [P-01], Popular Make Page [P-02], Overall Rating Page [P-06]
F-08 | LogOut | Home Page [P-01], Popular Make Page [P-02], Car Voting Page [P-03], Profile Page [P-04], Registration Page [P-05], Overall Rating Page [P-06]

## F01-Authentication
Risk ID | Risk / What Could Go Wrong | Rationale | Likelihood | Priority | Impact
AUTH-R01 | User may be unable to enter credentials into the Login or Password fields | Prevents the user from attempting authentication | Low | High | High
AUTH-R02 | Login button may not initiate authentication when clicked | Prevents the user from submitting credentials | Low | High | High
AUTH-R03 | Invalid credential combinations may successfully authenticate the user | Could allow unauthorized access | Unknown | High | Critical
AUTH-R04 | Valid credentials may fail to authenticate the user | Prevents legitimate users from accessing authenticated functionality | Medium | High | High
AUTH-R05 | Failed authentication may display incorrect, unclear, or no failure message | User may not understand that authentication failed or why | Medium | Medium | Medium
AUTH-R06 | Successful authentication may result in an incorrect page/application state | User may be authenticated but remain in an inappropriate state or page | High | Medium | Medium

## F02-Registration
Risk ID | Risk / What Could Go Wrong | Rationale | Likelihood | Impact | Priority
REG-R01 | Required name fields may accept missing or invalid values | Could allow incomplete or invalid user accounts to be created | Medium | Medium | Medium
REG-R02 | Name fields may incorrectly reject valid values | Could prevent legitimate users from registering | Medium | Medium | Medium
REG-R03 | Registration may incorrectly handle duplicate user-identifying values | Could create conflicting accounts or incorrectly prevent legitimate registration | Unknown | High | High
REG-R04 | Login/email field may accept invalidly formatted values | Could create accounts with unusable or invalid identifiers | Medium | High | High
REG-R05 | Valid login/email values may be incorrectly rejected | Could prevent legitimate users from registering | Medium | High | High
REG-R06 | Password may accept values that do not satisfy required password rules | Could create accounts with passwords that violate the application's intended validation rules | Unknown | High | High
REG-R07 | Valid passwords may be incorrectly rejected | Could prevent legitimate account creation | Medium | Medium | Medium
REG-R08 | Password and Confirm Password may not be validated against each other | Could create an account with an unintended password or produce inconsistent registration behaviour | Medium | High | High
REG-R09 | Registration inputs may not safely handle unexpected or malicious input | Unexpected input could cause incorrect behaviour, errors, or unsafe processing | Unknown | High | High
REG-R10 | Invalid registration attempts may display missing, incorrect, or unclear validation/status messages | Users may not understand which input is invalid or how to correct it | Medium | Medium | Medium
REG-R11 | Valid registration details may fail to create an account | Prevents legitimate users from registering | Medium | High | High
REG-R12 | Registration submission may fail to initiate when the Register button is used | Prevents users from completing registration | Low | High | High

## F03-CarBrowsing&Navigation
Risk ID | Risk / What Could Go Wrong | Rationale | Likelihood | Impact | Priority
BROWSE-R01 | Car model name and displayed image may not correspond to the same car | Users may be shown misleading or incorrect vehicle information | Medium | Medium | Medium
BROWSE-R02 | Selecting a car model may navigate to the wrong Car Voting page | User may view or interact with a different model than the one selected | Medium | High | High
BROWSE-R03 | View More may navigate to the wrong car model | User may access comments/details belonging to another model | Medium | High | High
BROWSE-R04 | Next/Previous pagination may not change the displayed result set | Users may be unable to browse beyond the current set of cars | Medium | Medium | Medium
BROWSE-R05 | Pagination may skip or duplicate car models between pages | Users may not be able to access the complete car list | Medium | Medium | Medium
BROWSE-R06 | Navigation links may leave the user on the current page or navigate to an incorrect page | Core application navigation may become unreliable | Medium | High | High

## F04-Voting&Comments
Risk ID | Risk / What Could Go Wrong | Rationale | Likelihood | Impact | Priority
VOTE-R01 | Unauthenticated users may be able to submit votes | Could allow unauthorized voting and compromise vote integrity | Unknown | High | High
VOTE-R02 | Unauthenticated users may be able to submit comments | Could allow unauthorized content submission | Unknown | High | High
VOTE-R03 | An authenticated user may be able to vote for the same car model more than once when repeat voting is not permitted | Could manipulate vote counts and model rankings | High | High | High
VOTE-R04 | Voting restrictions may be bypassed by refreshing or leaving and returning to the page | Client/page state may reset while the underlying voting restriction should remain enforced | High | High | High
VOTE-R05 | A user who logs out while remaining on the Car Voting Page [P-03] may still be able to vote or comment | Previously loaded authenticated controls may remain usable after the session ends | Medium | High | High
VOTE-R06 | Excessively long comments may break or significantly disrupt the comments layout | Could reduce readability or make the page difficult to use | Medium | Medium | Medium
VOTE-R07 | Special or unexpected characters in comments may render incorrectly or disrupt the page layout | Could cause malformed display or incorrect handling of submitted content | Medium | Medium | Medium
VOTE-R08 | A submitted vote may not correctly update the displayed vote count | Users may see inaccurate voting information | Medium | High | High
VOTE-R09 | A submitted comment may not be saved or displayed correctly | User-submitted content could be lost, altered, or associated incorrectly | Medium | Medium | Medium
VOTE-R10 | Vote/comment submission may provide incorrect, unclear, or no confirmation | Users may not know whether their submission succeeded | Medium | Medium | Medium

## F05-ProfileManagement
Risk ID | Risk / What Could Go Wrong | Rationale | Likelihood | Impact | Priority
PROF-R01 | Profile changes may not be saved correctly | Users may lose changes or have incorrect profile information stored | Medium | Medium | Medium
PROF-R02 | Profile fields may accept invalid or unsupported values | Invalid user data could be stored | Medium | Medium | Medium
PROF-R03 | Age may accept implausible or invalid values | Could result in invalid profile information | Medium | Low | Low
PROF-R04 | Gender may accept unsupported values or valid values may be incorrectly rejected | Profile data may not comply with the application's intended rules | Medium | Medium | Medium
PROF-R05 | Dropdown fields may accept values outside their available options | Could bypass intended input restrictions | Low | Medium | Low
PROF-R06 | Selected dropdown values may not be saved correctly | User selections could be lost or incorrectly stored | Medium | Medium | Medium
PROF-R07 | Clicking Cancel may save modifications instead of discarding them | Users could unintentionally modify their profile | Low | Medium | Low
PROF-R08 | Previously saved profile information may not load correctly | Users may see outdated, missing, or incorrect information | Medium | Medium | Medium
PROF-R09 | Read-only account information such as Login may be modified when it should not be editable | Account identifiers could be unintentionally changed | Low | High | Medium

## F06-PasswordManagement
Risk ID | Risk / What Could Go Wrong | Rationale | Likelihood | Impact | Priority
PASS-R01 | Password may be changed without providing the correct current password | An unauthorized person with access to an active session could change the account password | Unknown | High | High
PASS-R02 | New Password and Confirm Password may not be required to match | User could unknowingly set a password different from what they intended | Medium | High | High
PASS-R03 | Invalid or unsupported passwords may be accepted | Could allow passwords that violate the application's intended password rules | Medium | High | High
PASS-R04 | Valid passwords may be incorrectly rejected | Users could be prevented from changing their password | Medium | Medium | Medium
PASS-R05 | Empty password fields may unintentionally modify the existing password | The UI states “leave empty to keep current,” so leaving them empty should preserve the password | Medium | High | High
PASS-R06 | Incorrect or unclear status messages may be shown when password change fails | Users may not understand why the password change was unsuccessful | Medium | Medium | Medium
PASS-R07 | Password change may appear successful but the new password may not actually be stored | User could later be unable to authenticate using the expected new password | Medium | High | High
PASS-R08 | Old password may remain usable after a successful password change | Password update may not be applied correctly | Medium | High | High

## F07-RankingManagement
Risk ID | Risk / What Could Go Wrong | Rationale | Likelihood | Impact | Priority
RANK-R01 | Car rankings may not be sorted correctly according to vote count | Displayed ranking may not accurately represent the cars' vote totals | Medium | High | High
RANK-R02 | Displayed rank may not correspond with the car's position in the ranking | Users may see inconsistent ranking information | Medium | Medium | Medium
RANK-R03 | Vote count displayed in ranking pages may differ from the vote count on the corresponding Car Voting page | The same car may show inconsistent rating data across the application | Medium | High | High
RANK-R04 | Ranking may not update correctly after a new vote is submitted | Recently submitted votes may not be reflected in the displayed ranking | Medium | High | High
RANK-R05 | The same car may show different rank/vote information across Home, Popular Make and Overall Rating | Users may receive contradictory rating information depending on the page viewed | Medium | High | High

## F08-LogOut
Risk ID | Risk / What Could Go Wrong | Rationale | Likelihood | Impact | Priority
SES-R01 | Logout may not properly terminate the authenticated session | User may remain authenticated after requesting logout | Unknown | High | High
SES-R02 | Protected user information may remain visible after logout | Sensitive account information may remain accessible after the session ends | High | High | High
SES-R03 | User may still be able to perform authenticated actions after logout | Protected operations such as profile updates or voting could remain accessible | Medium | High | High
SES-R04 | Logging out may leave the user on a protected page instead of moving to an appropriate logged-out state/page | The page may remain in an inconsistent authenticated/logged-out state | High | Medium | High
SES-R05 | Refreshing or revisiting a protected page after logout may restore authenticated access | Session termination may not persist correctly | Medium | High | High
SES-R06 | Logout behaviour may be inconsistent depending on which page the user logs out from | Session handling may differ across the application | Medium | Medium | Medium

## Master Risks
Risk ID | Risk / What Could Go Wrong | Rationale | Likelihood | Priority | Impact
AUTH-R01 | User may be unable to enter credentials into the Login or Password fields | Prevents the user from attempting authentication | Low | High | High
AUTH-R02 | Login button may not initiate authentication when clicked | Prevents the user from submitting credentials | Low | High | High
AUTH-R03 | Invalid credential combinations may successfully authenticate the user | Could allow unauthorized access | Unknown | High | Critical
AUTH-R04 | Valid credentials may fail to authenticate the user | Prevents legitimate users from accessing authenticated functionality | Medium | High | High
AUTH-R05 | Failed authentication may display incorrect, unclear, or no failure message | User may not understand that authentication failed or why | Medium | Medium | Medium
AUTH-R06 | Successful authentication may result in an incorrect page/application state | User may be authenticated but remain in an inappropriate state or page | High | Medium | Medium
REG-R01 | Required name fields may accept missing or invalid values | Could allow incomplete or invalid user accounts to be created | Medium | Medium | Medium
REG-R02 | Name fields may incorrectly reject valid values | Could prevent legitimate users from registering | Medium | Medium | Medium
REG-R03 | Registration may incorrectly handle duplicate user-identifying values | Could create conflicting accounts or incorrectly prevent legitimate registration | Unknown | High | High
REG-R04 | Login/email field may accept invalidly formatted values | Could create accounts with unusable or invalid identifiers | Medium | High | High
REG-R05 | Valid login/email values may be incorrectly rejected | Could prevent legitimate users from registering | Medium | High | High
REG-R06 | Password may accept values that do not satisfy required password rules | Could create accounts with passwords that violate the application's intended validation rules | Unknown | High | High
REG-R07 | Valid passwords may be incorrectly rejected | Could prevent legitimate account creation | Medium | Medium | Medium
REG-R08 | Password and Confirm Password may not be validated against each other | Could create an account with an unintended password or produce inconsistent registration behaviour | Medium | High | High
REG-R09 | Registration inputs may not safely handle unexpected or malicious input | Unexpected input could cause incorrect behaviour, errors, or unsafe processing | Unknown | High | High
REG-R10 | Invalid registration attempts may display missing, incorrect, or unclear validation/status messages | Users may not understand which input is invalid or how to correct it | Medium | Medium | Medium
REG-R11 | Valid registration details may fail to create an account | Prevents legitimate users from registering | Medium | High | High
REG-R12 | Registration submission may fail to initiate when the Register button is used | Prevents users from completing registration | Low | High | High
BROWSE-R01 | Car model name and displayed image may not correspond to the same car | Users may be shown misleading or incorrect vehicle information | Medium | Medium | Medium
BROWSE-R02 | Selecting a car model may navigate to the wrong Car Voting page | User may view or interact with a different model than the one selected | Medium | High | High
BROWSE-R03 | View More may navigate to the wrong car model | User may access comments/details belonging to another model | Medium | High | High
BROWSE-R04 | Next/Previous pagination may not change the displayed result set | Users may be unable to browse beyond the current set of cars | Medium | Medium | Medium
BROWSE-R05 | Pagination may skip or duplicate car models between pages | Users may not be able to access the complete car list | Medium | Medium | Medium
BROWSE-R06 | Navigation links may leave the user on the current page or navigate to an incorrect page | Core application navigation may become unreliable | Medium | High | High
VOTE-R01 | Unauthenticated users may be able to submit votes | Could allow unauthorized voting and compromise vote integrity | Unknown | High | High
VOTE-R02 | Unauthenticated users may be able to submit comments | Could allow unauthorized content submission | Unknown | High | High
VOTE-R03 | An authenticated user may be able to vote for the same car model more than once when repeat voting is not permitted | Could manipulate vote counts and model rankings | High | High | High
VOTE-R04 | Voting restrictions may be bypassed by refreshing or leaving and returning to the page | Client/page state may reset while the underlying voting restriction should remain enforced | High | High | High
VOTE-R05 | A user who logs out while remaining on the Car Voting Page [P-03] may still be able to vote or comment | Previously loaded authenticated controls may remain usable after the session ends | Medium | High | High
VOTE-R06 | Excessively long comments may break or significantly disrupt the comments layout | Could reduce readability or make the page difficult to use | Medium | Medium | Medium
VOTE-R07 | Special or unexpected characters in comments may render incorrectly or disrupt the page layout | Could cause malformed display or incorrect handling of submitted content | Medium | Medium | Medium
VOTE-R08 | A submitted vote may not correctly update the displayed vote count | Users may see inaccurate voting information | Medium | High | High
VOTE-R09 | A submitted comment may not be saved or displayed correctly | User-submitted content could be lost, altered, or associated incorrectly | Medium | Medium | Medium
VOTE-R10 | Vote/comment submission may provide incorrect, unclear, or no confirmation | Users may not know whether their submission succeeded | Medium | Medium | Medium
PROF-R01 | Profile changes may not be saved correctly | Users may lose changes or have incorrect profile information stored | Medium | Medium | Medium
PROF-R02 | Profile fields may accept invalid or unsupported values | Invalid user data could be stored | Medium | Medium | Medium
PROF-R03 | Age may accept implausible or invalid values | Could result in invalid profile information | Medium | Low | Low
PROF-R04 | Gender may accept unsupported values or valid values may be incorrectly rejected | Profile data may not comply with the application's intended rules | Medium | Medium | Medium
PROF-R05 | Dropdown fields may accept values outside their available options | Could bypass intended input restrictions | Low | Medium | Low
PROF-R06 | Selected dropdown values may not be saved correctly | User selections could be lost or incorrectly stored | Medium | Medium | Medium
PROF-R07 | Clicking Cancel may save modifications instead of discarding them | Users could unintentionally modify their profile | Low | Medium | Low
PROF-R08 | Previously saved profile information may not load correctly | Users may see outdated, missing, or incorrect information | Medium | Medium | Medium
PROF-R09 | Read-only account information such as Login may be modified when it should not be editable | Account identifiers could be unintentionally changed | Low | High | Medium
PASS-R01 | Password may be changed without providing the correct current password | An unauthorized person with access to an active session could change the account password | Unknown | High | High
PASS-R02 | New Password and Confirm Password may not be required to match | User could unknowingly set a password different from what they intended | Medium | High | High
PASS-R03 | Invalid or unsupported passwords may be accepted | Could allow passwords that violate the application's intended password rules | Medium | High | High
PASS-R04 | Valid passwords may be incorrectly rejected | Users could be prevented from changing their password | Medium | Medium | Medium
PASS-R05 | Empty password fields may unintentionally modify the existing password | The UI states “leave empty to keep current,” so leaving them empty should preserve the password | Medium | High | High
PASS-R06 | Incorrect or unclear status messages may be shown when password change fails | Users may not understand why the password change was unsuccessful | Medium | Medium | Medium
PASS-R07 | Password change may appear successful but the new password may not actually be stored | User could later be unable to authenticate using the expected new password | Medium | High | High
PASS-R08 | Old password may remain usable after a successful password change | Password update may not be applied correctly | Medium | High | High
RANK-R01 | Car rankings may not be sorted correctly according to vote count | Displayed ranking may not accurately represent the cars' vote totals | Medium | High | High
RANK-R02 | Displayed rank may not correspond with the car's position in the ranking | Users may see inconsistent ranking information | Medium | Medium | Medium
RANK-R03 | Vote count displayed in ranking pages may differ from the vote count on the corresponding Car Voting page | The same car may show inconsistent rating data across the application | Medium | High | High
RANK-R04 | Ranking may not update correctly after a new vote is submitted | Recently submitted votes may not be reflected in the displayed ranking | Medium | High | High
RANK-R05 | The same car may show different rank/vote information across Home, Popular Make and Overall Rating | Users may receive contradictory rating information depending on the page viewed | Medium | High | High
SES-R01 | Logout may not properly terminate the authenticated session | User may remain authenticated after requesting logout | Unknown | High | High
SES-R02 | Protected user information may remain visible after logout | Sensitive account information may remain accessible after the session ends | High | High | High
SES-R03 | User may still be able to perform authenticated actions after logout | Protected operations such as profile updates or voting could remain accessible | Medium | High | High
SES-R04 | Logging out may leave the user on a protected page instead of moving to an appropriate logged-out state/page | The page may remain in an inconsistent authenticated/logged-out state | High | Medium | High
SES-R05 | Refreshing or revisiting a protected page after logout may restore authenticated access | Session termination may not persist correctly | Medium | High | High
SES-R06 | Logout behaviour may be inconsistent depending on which page the user logs out from | Session handling may differ across the application | Medium | Medium | Medium